## Sheet1
Project Risks
Design | Initial risk | Current risk | Art | Initial risk | Current risk
Coming up with original creature designs | Red |  | Creating creatures which all have the same type of art style and aesthetic | Red
Deciding on font for text in the game | Amber |  | Creating all the different animations we will need within the game | Red
Deciding on type of sounds we want in the game | Amber |  | Creating journal opening animation | Amber
Having unique egg designs | Red |  | Creating seed to tree growing animation | Amber
Coming up with an original journal index | Red
Coming up with relevant creature bio descriptions | Amber
Creating an updated crafting screen menu which suits the games aesthetic | Red
Source sound for opening screen | Red
Source sound for background music | Red
Source sound for egg hatching | Amber
Source sound for planting a seed | Amber
Source sound for seed completing growth to a tree | Amber
Source sound for tree death | Amber
Source sound for discovering a new creature | Amber
Source sound for new creature being added to your journal | Amber
Creating new Island designs | Amber
Creating designs for creature bodies which are shaped to match the fruit they eat | Amber
Programming | Initial risk | Current risk | Publisher | Initial risk | Current risk | Marketing | Initial risk | Current risk
Implementing the variable reward schedules | Red |  | Convincing the publisher our game deserves funding | Red |  | Differentiating our game from other similar pet simulator games | Red
Implementing sounds into the game | Amber
Having creatures change saturation based on happiness | Red
Creating the Island section screen dial | Amber
Creating happyness meter for creating which reacts to what fruit you feed the creatures | Red
Implementing a statistics menu for the creatures, which can increase/level up | Red
Implement eggs changing colours after being dyed by fruit and spawning different creature | Red
Implement creatures mating by having an egg spawn when both creatures are together | Amber
Implement networking for creature contests | Red
Red
Amber
Green