## Sheet1
Project Risks
Design | Initial risk | Current risk | Art | Initial risk | Current risk
Coming up with original creature designs | Red |  | Creating creatures which all have the same type of art style and aesthetic | Red
Deciding on font for text in the game | Amber |  | Creating all the different animations we will need within the game | Red
Deciding on type of sounds we want in the game | Amber
Having unique egg designs | Red
Programming | Initial risk | Current risk | Publisher | Initial risk | Current risk | Marketing | Initial risk | Current risk
Implementing the variable reward schedules | Red |  | Convincing publisher our game is unique | Red |  | Differentiating our game from other similar pet simulator games | Red
Implementing sounds into the game | Amber
Having creatures change saturation based on happiness | Red
Creating the Island section screen dial | Amber
Red
Amber
Green